StayPulse

Project Planning

Phase 2: Project Planning

| Item | Details |
| --- | --- |
| Project | StayPulse: Hotel Booking and Property Management Web Application (MERN stack) |
| Phase | Phase 2: Project Planning |
| Document | Project Planning |
| Version / date | 1.0, 28 October 2026 |
| Basis | Inspection of the uploaded StayPulse source repository. Statements are tagged as implemented, partial, proposed, assumption, or not verified. |

Note on dates: The repository contains no project schedule, commit history or time log. The timeline in Section 6 is a proposed plan for a 10-week academic project. It does not record when work actually took place. The "Repository evidence" column states what exists in the source today.

# 1. Project Overview

StayPulse is a MERN stack hotel booking and property management application with three roles: Guest, Property Owner and Platform Admin. New property listings require administrator approval before they are public. Bookings are demonstrations without payment processing.

# 2. Project Objectives

- Deliver property discovery, room details and availability checking for guests.

- Deliver booking and cancellation with conflict-free reservations.

- Deliver owner tools for properties, rooms, pricing and reservations.

- Deliver an admin approval and moderation workflow.

- Secure the system with JWT authentication, role-based access and input validation.

- Verify the work through automated backend tests and user acceptance testing.

- Produce phase-wise documentation.

# 3. Scope and Exclusions

| In scope | Exclusions |
| --- | --- |
| Frontend SPA (React, Vite, Tailwind CSS) REST API (Node.js, Express) MongoDB data model (Mongoose) Three-role access control Local image upload Seed scripts for admin and demo data Backend automated tests | Real payments and refunds Email or SMS notifications Reviews and ratings Password reset and email verification Cloud storage, CI/CD and production deployment Frontend automated tests (none present) |

# 4. Major Development Phases

| Phase | Purpose | Main output |
| --- | --- | --- |
| P1 Ideation | Define idea, problems and users | Ideation documents |
| P2 Planning | Plan scope, work, risks | This document |
| P3 Requirement analysis | Requirements, data flows, technology | DFDs, FR/NFR, technology stack |
| P4 Design | Solution, architecture, data model | Design documents |
| P5 Implementation | Build backend and frontend | Source code |
| P6 Testing and acceptance | Automated tests and UAT | Test suite, UAT record |

Source comments in the frontend refer to numbered development phases (for example, "Phase 2 UI development"), but no mapping to dates exists. This plan does not claim how those phases align with the phases above.

# 5. Work Breakdown Structure

Table 1: Work breakdown structure with repository evidence

| WBS | Work package | Repository evidence | Status |
| --- | --- | --- | --- |
| 1.0 | Project management and documentation | README.md, docs/ARCHITECTURE.md, docs/PORTFOLIO_DEMO.md | Implemented |
| 2.0 | Requirements and design | Architecture documentation and models | Implemented |
| 3.1 | Backend: authentication and RBAC | authController, auth.js, token.js | Implemented |
| 3.2 | Backend: properties, rooms, approval | propertyController, roomController, adminController | Implemented |
| 3.3 | Backend: booking engine and slots | bookingController, RoomReservationSlot model | Implemented |
| 3.4 | Backend: image upload and privacy | uploadRoutes, fileUpload.js | Implemented |
| 3.5 | Backend: seed scripts | seedAdmin.js, seedData.js, updateAdminName.js | Implemented |
| 4.1 | Frontend: public pages | HomePage, HotelListingPage, HotelDetailsPage | Implemented |
| 4.2 | Frontend: auth and role guards | LoginPage, RegisterPage, AuthContext, ProtectedRoute | Implemented (mock sandbox present) |
| 4.3 | Frontend: guest, owner, admin dashboards | pages/dashboard/* | Implemented; admin settings Partial |
| 5.1 | Backend automated tests | 6 files in backend/tests (92 test declarations) | Implemented; results not re-run |
| 5.2 | Frontend automated tests | None found | Not present |
| 5.3 | User acceptance testing | See UAT document | Pending Verification |
| 6.0 | Deployment and CI/CD | No configuration found | Proposed |

# 6. Proposed Timeline and Milestones

Table 2: Proposed 10-week plan (not a record of actual dates)

| Week | Activities | Milestone (proposed) |
| --- | --- | --- |
| 1 | Ideation, problem statements, empathy maps | M1: Ideation documents approved |
| 2 | Requirements, DFDs, technology selection, scope freeze | M2: Requirements baseline |
| 3 | Design: architecture, data model, API outline | M3: Design baseline |
| 4 | Backend foundation: models, authentication, RBAC | M4: Auth API working |
| 5 | Property, room and approval APIs | M5: Listing workflow working |
| 6 | Booking engine, availability, concurrency handling | M6: Booking API working |
| 7 | Frontend public pages, auth screens | M7: Guest journey on UI |
| 8 | Owner and admin dashboards, uploads, privacy rules | M8: Feature complete |
| 9 | Automated tests, UAT execution, defect fixing | M9: UAT sign-off |
| 10 | Final documentation and demonstration | M10: Submission |

# 7. Required Tools and Resources

| Category | Resource | Source |
| --- | --- | --- |
| Languages and runtime | JavaScript (ES modules), Node.js 18 or later | README |
| Frontend | React 18, Vite 6, Tailwind CSS 3, React Router 6, Axios | package.json |
| Backend | Express 4, Mongoose 8, JWT, bcryptjs, helmet, multer | package.json |
| Database | MongoDB (local or Atlas) | README |
| Testing | Node.js built-in test runner | package.json |
| Other | Code editor, Git, browser, API client (for example, curl) | Assumption |
| People | Student developer(s), reviewer | Assumption |

# 8. Risks and Mitigation

| ID | Risk | Likelihood / impact | Mitigation (existing or proposed) |
| --- | --- | --- | --- |
| R1 | Double booking under concurrent requests | Medium / High | Unique (room, date) slot index with leased locks (implemented) |
| R2 | Standalone MongoDB lacks multi-document transactions | Low / Medium | Slot lease expiry and compensating rollback (implemented); use a replica set in production (proposed) |
| R3 | Weak secret configuration (JWT fallback secret exists in code) | Medium / High | Require JWT_SECRET at start-up (proposed) |
| R4 | Tests run against the configured development database | Medium / Medium | Use a separate test database URI (proposed) |
| R5 | Mock sandbox in the frontend mistaken for real authentication | Medium / Medium | Remove or disable in production builds (proposed) |
| R6 | Scope creep (payments, notifications) | Medium / Medium | Keep exclusions list; treat as future work |
| R7 | Local file storage does not scale | Low / Medium | Move to cloud storage in future (proposed) |
| R8 | Limited time for UAT | Medium / Medium | Prioritise high-risk cases first |

# 9. Deliverables

- Source code (frontend and backend) and seed scripts.

- Backend automated test suite.

- Eleven phase-wise documents in the Documentation folder.

- UAT record to be completed by executing the listed cases.

# 10. Completion Criteria

- All high-priority functional requirements implemented and traceable to code.

- Backend test suite run with all tests passing and results recorded (not yet verified in this documentation exercise).

- All UAT cases executed with results recorded; no open critical defects.

- Documentation reviewed and consistent with the code.

## Status legend

| Tag | Meaning |
| --- | --- |
| Implemented | Supported by code in the repository (verified by reading the source). |
| Partial | Present in code but incomplete, UI-only, or not wired end to end. |
| Proposed | Not in the repository; suggested for future work or planning. |
| Assumption | A reasonable statement not verifiable from the repository. |
| Not Verified | Could not be confirmed (for example, tests that were not executed). |